Delivery Schedule

Project Delivery schedule

The supplier will complete the entire job until FAC (as per the scope of work & technical specification)

Robi’s timeline proposal as follows, mentioned timeline is maximum, vendor can be share the better schedule.

Local/Locally Available items & Services (Like Electrical DB, Substation, accessories & Service)

|  | Task | Days | Comply/Remarks |
| --- | --- | --- | --- |
| PO issuance |  | D0=Date of PO issuance |  |  |
| Delivery |  | D1=D0 + 15 Days |  |  |
| Site Rollout |  | D2=D1+ 3 Weeks |  |  |
| User acceptance (UAT) & PAC |  | D3= D2 + 1 Week |  |  |
| FAC |  | D4= D3 + 1 Week |  |  |

Foreign items (Like SRF, SPD, LA, Higher capacity Breakers etc)

|  | Task | Days | Comply/Remarks |
| --- | --- | --- | --- |
| PO issuance |  | D0=Date of PO issuance |  |  |
| Delivery |  | D1=D0 + 60 Days |  |  |
| Site Rollout |  | D2=D1+ 3 Weeks |  |  |
| User acceptance (UAT) & PAC |  | D3= D2 + 1 Week |  |  |
| FAC |  | D4= D3 + 1 Week |  |  |

Civil Design

| Task | Days |  | Comply/Remarks |
| --- | --- | --- | --- |
| Survey and soil test report |  | 15 days from PO |  |  |
| All design report |  | 15 days from PO |  |  |
| BUET Approval |  | 30 days from PO |  |  |
| NOC from Govt Authority |  | 45 days from PO |  |  |

AFPS System

| Task | Days |  | Remarks |
| --- | --- | --- | --- |
| PO issuance |  | D0=Date of PO issuance |  |  |
| Delivery |  | D1=D0 + 10 Weeks |  |  |
| Site Rollout |  | D2=D1+ 2 Weeks |  |  |
| User acceptance (UAT) & PAC |  | D3= D2 + 1 Week |  |  |
| FAC |  | D4= D3 + 1 Week |  |  |