## Issue Log REVISED
eSourcing Platform – ISSUE/CR TRACKER
Re-started from 1st July 2026
Issue ID | Raised on | Module/Section | Issue Title | Detailed Description | Reference / Screen | Raised by | Type | Assinged to for resolution | Resolved on | Root Cause | Current Responsible Person | Current Status
Y26/001 | 2026-08-12 | eSourcing Platform | Draft Event Deletion | Before we can delete Draft Event, now I don’t see that option. Would you please check the option and let us know. | For example, we wanted to delete the 4332-Round.0 from PRD. | Mahabub, Robi, SCM | Issue | Fahim |  |  | Fahim | Open
Y26/002 | 2026-08-11 | eSourcing Platform | Response Item' | What is the function of ‘Response Items’ Tab. Please discuss. | email dated 11 August, 2026 11:55 AM with image | Mahabub, Robi, SCM | Information | Fahim |  |  | Fahim | Open
Y26/003 | 2026-08-11 | eSourcing Platform | History / Audit Trail | Previous History is Showing in the copied Event (new) | email dated 11 August, 2026 11:52 AM with image. Demo Event on Forward Auction for FLT 20260811 #2168-Round.0 in TEST Server | Mahabub, Robi, SCM | Issue | Fahim |  |  | Fahim | Open
Y26/004 | 2026-08-11 | eSourcing Platform | Test Server Identification | Please insert a label in the TEST Server, so that we can understand that it Test Server instantly. | email dated 11 August, 2026 11:16 AM. | Mahabub, Robi, SCM | Change Request | Fahim |  |  | Fahim | Open
Y26/005 | 2026-08-05 | eSourcing Platform | Event Visibility by the Bidder | Bidder can see the Draft Event that is in Owner end (next round) and not yet sent to Bidder for participate. | Explained | Kawser, Robi, SCM | Issue | Fahim | 2026-08-10 | DRAFT event visibility access was given to Bidders mistakenly. | Fahim | Closed
Y26/006 | 2026-07-31 | Forward Auction | Offer Submiited Info | Offer is not submitted but showing Offer Submitted 1 (JR - second line) | email dated Friday, July 31, 2026 12:18 PM | Mahabub, Robi, SCM | Issue | Fahim |  |  | Fahim | Open
Y26/007 | 2026-07-31 | Forward Auction | Auction Rules | Specify how item bidding will begin and end in Event Preview - NOT showing | email dated Friday, July 31, 2026 7:05 AM | Mahabub, Robi, SCM | Issue | Fahim | 2026-07-31 |  | Fahim | Closed
Y26/008 | 2026-07-31 | Forward Auction | Event Visibility by the Bidder | Last seen record in Draft Event | email dated Friday, July 31, 2026 6:49 AM | Mahabub, Robi, SCM | Issue | Fahim |  |  | Fahim | Open
Y26/009 | 2026-07-31 | Forward Auction | Pricing Title and Preview before Submit Event | In the Forward Auction title is still ceiling amount (Buyer side) and it is not showing in the preview | email dated Friday, July 31, 2026 7:04 AM | Mahabub, Robi, SCM | Issue | Fahim |  |  | Fahim | Open
Y26/010 | 2026-07-09 | Report | Event and its Round Visibility | Under an event, how can we see all versions and all bidders’ bids (offers). | email dated Thu 09-Jul-26 11:02 AM | Mahabub, Robi, SCM | UAT | Fahim |  |  | Fahim | Open
Y26/011 | 2026-08-12 | Ticketing Tool | Ticketing Tool User ID and PW | User ID and PW for raising ticket in the Portal for Robi eSourcing Platform issues | Discussed in the Meeting on 12th Aug 2026 | Mahabub, Robi, SCM | Support | Sohel |  |  | Sohel | Open
Y26/012 | 2026-08-12 | eSourcing Platform | Notification Management | Notification Management is not working. Robi will create 2 dummy vendors and test. | Discussed in the Meeting on 12th Aug 2026 | Mahabub, Robi, SCM | Issue | Mahabub |  |  | Mahabub | Open
Y26/013 | 2026-08-12 | eSourcing Platform | User Manual | Review and update User Manual for Robi and Bidders | Discussed in the Meeting on 12th Aug 2026 | Mahabub, Robi, SCM | Support | Fahim |  |  | Fahim | Open
Y26/013 | 2026-08-12 | eSourcing Platform | Feature Enhancement including AI enables if any. | Both Team will explore feature in addition of core eSourcing Platform including AI/Automation/Risk/Compliance to reduce time and effort as per Robi Management Expectation. Proposal will be submitted to Robi Management after sorting the list along with limitation and tetative costing. | Discussed in the Meeting on 12th Aug 2026 | Mahabub, Robi, SCM | Support | Sohel |  |  | Sohel | Open

## Issue Log
eSourcing Platform – Forward Auction ¦ UAT ISSUE TRACKER
UAT conducted 08-Jul-2026 · Observations after fixing issues · Yellow-tinted columns (Status, Assigned To, Target Date, Closed Date, Remarks) are to be updated by the project team.
Issue ID | Module | Issue Title | Detailed Description | Reference / Screen | Type | Status
UAT-001 | Event Setup | Non-functional field to be hidden | The marked function/field on the event creation screen does not appear to be working. Confirm whether it is functional; if not, hide it from the interface. | Event Creation screen | Enhancement | Closed
UAT-002 | Event Setup – Notification | Incorrect label: 'Also Notify Buyer?' | Change the label 'Also Notify Buyer?' to 'Notify Event Creator' so it reflects the actual recipient. | Event Notification settings | UI / Label | Closed
UAT-003 | Event Setup | Amount fields not formatted as currency | The marked amount fields must be displayed in currency format (thousand separator + decimals + currency symbol). | Event Creation screen | UI / Formatting | Closed
UAT-004 | Bidder Interface | 'Lead Bid Calculation' button missing | Bidders need a 'Lead Bid Calculation' button so they can calculate the value required to win the bid before submission. Required for both Reverse and Forward Auctions. | Bidder bidding screen | New Feature | Deferred
UAT-005 | Auction Conditions | Clarify whether all auction conditions are mandatory | Confirm whether every auction condition is mandatory. If mandatory, the system must not allow the field to be saved blank — add validation. | Auction Conditions setup | Clarification / Validation | Closed
UAT-006 | Auction Conditions | Blank condition displays values to bidder; values mismatch | A condition left blank at setup is showing values in the bidder's window, and values for other conditions do not match what was configured. | Event # Test on Forward Auction 4 #2165 – Round.0 | Defect | Closed
UAT-007 | Graph / Visualisation | Show time only on axis, displayed vertically | The bid graph should display time only (no dates), with the axis labels shown vertically. | Live auction bid graph | Enhancement | Closed
UAT-008 | Graph / Visualisation | Auto-grid required for high bid volume | When many bids are received, the graph must auto-adjust its grid/scale to remain readable. | Live auction bid graph | Enhancement | Closed
UAT-009 | Graph / Visualisation | Show bid value tooltip on hover | When the cursor is placed on a data point, the bid value label must be displayed. | Live auction bid graph | Enhancement | Closed
UAT-010 | Bidding | Bid increment % calculated incorrectly | Last bid was 37,000; on attempting to place 38,000 the system warned the bid was 94.87% higher. The percentage calculation is wrong (expected ~2.70%). | Bidder bid submission – warning message | Defect | Closed
UAT-011 | Unsealing | Auto unsealing not working | The automatic unsealing of bids at the scheduled time is not triggering. | Buyer – Unsealing | Defect | Closed
UAT-012 | Unsealing | Price shows 0.00 after unsealing | After the bids are unsealed no price is displayed; all values show as 0.00 instead of the submitted bid amounts. | Buyer – Unsealing / Bid summary | Defect | Closed
UAT-013 | Evaluation | Amount shown incorrectly in Evaluation | The bid amount carried into the Evaluation screen does not match the amount submitted by the bidder. | Evaluation screen | Defect | Closed
UAT-014 | Evaluation / Award | Award % shows 100 for all bidders with no amount | All bidders show 100% award with no amount displayed; award cannot be made without an amount. Recommend showing the evaluation score in line with the award allocation. | Evaluation / Award screen | Defect | Closed
UAT-015 | Evaluation / Award | Default 100% remains active after full award; '%' duplicated | Once 100% has been awarded, the default 100 field must become inactive. The '%' symbol is also being displayed twice. | Evaluation / Award screen | Defect | Closed
UAT-016 | Event Workflow | Event status remains 'Evaluation' after award | After evaluation is completed and the event is awarded, the event status still displays 'Evaluation' instead of moving to 'Awarded'. | Event status / workflow | Defect | Fixed – Pending Retest
UAT-017 | Dashboard | All events show 'xx days remaining' regardless of deadline | The front dashboard shows days remaining for every event. After the deadline has passed it should display the event status instead. Days remaining is acceptable only until the deadline. | Front dashboard | Enhancement | Deferred
UAT-018 | Task / Notification Template | Procedure to update Task information required | Clarify how Task information (notification/task templates) is updated and by whom — provide the configuration path. | Task / template configuration | Query | Open
UAT-019 | Task / Notification Template | Change OTP task subject line | Change the Subject to: 'OTP for Login Verification'. | OTP task / email template | Change Request | Closed
UAT-020 | History | Buyer / User activity not shown in History | Buyer and internal user activity should appear in the History log in the same way that Bidder/Supplier activity is shown. | Event History | Enhancement | Closed
UAT-021 | History | Supplier response / bid submission not logged in History | Supplier response and bid submission events must be recorded in the History log. | Event History | Enhancement | Closed
UAT-022 | Comprehensive Report | Missing field: Event Version | Add 'Event Version' to the Comprehensive Report. | Comprehensive Report output | Enhancement | Closed
UAT-023 | Comprehensive Report | Missing field: Event Currency | Add 'Event Currency' to the Comprehensive Report. | Comprehensive Report output | Enhancement | Closed
UAT-024 | Comprehensive Report | Missing field: Project Amount and Currency | Add 'Project Amount' and its currency to the Comprehensive Report. | Comprehensive Report output | Enhancement | Closed
UAT-025 | Comprehensive Report | Missing field: Event Type | Add 'Event Type' (RFI / RFQ / RFP / Reverse Auction / Forward Auction) to the Comprehensive Report. | Comprehensive Report output | Enhancement | Closed
UAT-026 | Comprehensive Report | Missing field: Event End Time | Add 'Event End Time' to the Comprehensive Report. | Comprehensive Report output | Enhancement | Closed
UAT-027 | Comprehensive Report | Savings amount calculation is wrong | The savings amount calculated in the Comprehensive Report is incorrect — logic to be reviewed and corrected. | Comprehensive Report output | Defect | Open
UAT-028 | Comprehensive Report | Missing field: Award % | Include the 'Award %' column in the Comprehensive Report. | Comprehensive Report output | Enhancement | Closed
UAT-029 | Comprehensive Report | Missing field: Event Team | Add 'Event Team' (e.g. Network Active Procurement) to the Comprehensive Report. | Comprehensive Report output | Enhancement | Closed